## Deliverables and Tasks
IMPORT SPEC
Deliverables and Tasks
Pale blue headers = import into SIGNAL now. Peach headers = reference only, for features not built yet (triggers, release, emails, follow-ups). Follow-ups apply to client tasks only. Every coach task has an optional time log.
Phase | Deliverable | Order | Task | Details / checklist | Type | Owner | Trigger | On done | Milestone | Client email | Send mode | Follow-up (days) | Calendly type | Land cap
Know | Your SIGNAL DNA Assessment | 1 | Book Your SIGNAL DNA Assessment |  | Client | Client | Released by welcome email (starts with Your SIGNAL DNA) | Creates prep task |  | #2 Welcome: starts with Your SIGNAL DNA | Preview | 3 | Your SIGNAL DNA Assessment
Know | Your SIGNAL DNA Assessment | 2 | Prepare for Your SIGNAL DNA Assessment |  | Coach | Peri | Booking made | Ready for session
Know | Your SIGNAL DNA Assessment | 3 | Run Your SIGNAL DNA Assessment | Live on Teams | Coach | Peri | Session held | Creates Prepare Your SIGNAL DNA report | Assessment complete
Know | Your SIGNAL DNA Report | 1 | Prepare Your SIGNAL DNA report | Review all responses, write report (10 sections, four paths, entry points, comparison table), add Decoder links (write missing pages) | Coach | Peri | Run assessment done | Library link added; releases Book Decode session | Report delivered | #6 Report ready + Decode booking link | Preview
Know | Your SIGNAL DNA Decode and Career Path Session | 1 | Book Decode session |  | Client | Client | Released by report email | Creates prep task |  | (sent by #6) |  | 3 | Your SIGNAL DNA Decode and Career Path (60 min)
Know | Your SIGNAL DNA Decode and Career Path Session | 2 | Prepare for Decode session |  | Coach | Peri | Booking made | Ready for session
Know | Your SIGNAL DNA Decode and Career Path Session | 3 | Run Decode session | Walk through report and path comparison, capture questions and reactions, confirm paths | Coach | Peri | Session held | Package continues into Build: releases Book Resume Workshop. Otherwise: closing email |  | #7 Decode recap + Resume Workshop link, or #23 closing email | Preview
Build | Resume Workshop | 1 | Book Resume Workshop | Upload instructions are in the welcome email | Client | Client | Released by #7, or by welcome email (starts with Resume Workshop) | Creates prep task |  | (sent by trigger) or #3 Welcome: starts with Resume Workshop | Preview | 3 | Resume Workshop
Build | Resume Workshop | 2 | Prepare for Resume Workshop | Review current resume, background, Decode paths | Coach | Peri | Booking made | Ready for session
Build | Resume Workshop | 3 | Run Resume Workshop | Define job paths together, confirm paths in writing | Coach | Peri | Session held | Creates Draft resume | Job paths defined
Build | Resume | 1 | Draft resume | Full rebuild line by line, variations by path, ATS structure check on all versions | Coach | Peri | Workshop done | Library link added; releases Review draft |  | #8 Draft resume ready + Finalize booking link | Edit and send
Build | Resume | 2 | Review draft and book Finalize session |  | Client | Client | Released by #8 | Creates prep task |  | (sent by #8) |  | 3 | Resume Review/Finalize
Build | Resume | 3 | Prepare for Finalize session |  | Coach | Peri | Booking made | Ready for session
Build | Resume | 4 | Run Resume Review/Finalize session |  | Coach | Peri | Session held | Releases Approve final resume |  | #9 Resume sign-off request | Preview
Build | Resume | 5 | Approve final resume | Client sign-off in Coaches Hub | Client | Client | Released by #9 | Creates Draft cover letter framework | Resume finalized |  |  | 3
Build | Cover Letter | 1 | Draft cover letter framework | Capture client voice, write custom cover letter, build reusable framework; walkthrough is in the email | Coach | Peri | Resume finalized | Library link added; releases Review cover letter |  | #10 Cover letter draft ready | Preview
Build | Cover Letter | 2 | Review and edit cover letter |  | Client | Client | Released by #10 | Creates Finalize cover letter |  | (sent by #10) |  | 3
Build | Cover Letter | 3 | Finalize cover letter | Back and forth by email, no session | Coach | Peri | Client review done | Releases Approve final cover letter |  | #11 Cover letter sign-off request | Preview
Build | Cover Letter | 4 | Approve final cover letter | Client sign-off in Coaches Hub | Client | Client | Released by #11 | History | Cover letter finalized |  |  | 3
Build | LinkedIn Rebuild | 1 | Build LinkedIn Rebuild plan | Headline, summary, experience, positioning | Coach | Peri | Coach starts | Library link added; releases Implement LinkedIn changes |  | #12 LinkedIn plan ready | Preview
Build | LinkedIn Rebuild | 2 | Implement LinkedIn changes |  | Client | Client | Released by #12 | Creates Review LinkedIn updates |  | (sent by #12) |  | 3
Build | LinkedIn Rebuild | 3 | Review LinkedIn updates | No client sign-off; coach review is enough | Coach | Peri | Client marks done | Approve: milestone. Changes needed: reopens Implement task (coach writes note personally) | LinkedIn complete
Search | SIGNAL Setup and Job Search Strategy | 1 | Book Job Search Strategy/Networking session |  | Client | Client | Released by coach, or by welcome email (starts with Search) | Creates prep task |  | #13 Book your strategy session, or #4 Welcome: starts with Search | Preview | 3 | Job Search Strategy/Networking
Search | SIGNAL Setup and Job Search Strategy | 2 | Prepare for strategy session | Update profile, create personas, enter target roles/locations/goals, seed 1 to 2 jobs (required) | Coach | Peri | Booking made | Ready for session
Search | SIGNAL Setup and Job Search Strategy | 3 | Run strategy session | Send SIGNAL invite live, full walkthrough, pursue and ignore rules, prioritization and sequencing, confirm campaign requirements | Coach | Peri | Session held | Creates Complete Client Brief | SIGNAL live | #14 SIGNAL invite | System, sent live
Search | Networking Campaign | 1 | Complete Client Brief | Built in SIGNAL | Coach | Peri | Strategy session done | Creates Build networking campaign; emails Erin
Search | Networking Campaign | 2 | Build networking campaign | 100 to 300 targeted professionals; workbook saved to client Drive. Built in SIGNAL | Coach | Erin | Client Brief done | Creates Review campaign; emails Peri
Search | Networking Campaign | 3 | Review campaign | Approve or request changes with feedback. Built in SIGNAL | Coach | Peri | Build done | Approve: creates Upload. Changes: reopens Build, emails Erin
Search | Networking Campaign | 4 | Upload campaign and build plan | Built in SIGNAL | Coach | Peri | Approved | Creates Share plan
Search | Networking Campaign | 5 | Share plan with client | Built in SIGNAL | Coach | Peri | Upload done | Library link added; releases Book Review Networking Plan |  | #15 Networking plan ready + Review Networking Plan link (add link) | Auto
Search | Networking Campaign | 6 | Book Review Networking Plan session | Client sends outreach from their own email | Client | Client | Released by #15 | Creates prep task |  | (sent by #15) |  | 3 | Review Networking Plan (30 min)
Search | Networking Campaign | 7 | Prepare for review session |  | Coach | Peri | Booking made | Ready for session
Search | Networking Campaign | 8 | Run Review Networking Plan session | No recap email | Coach | Peri | Session held | History | Campaign launched
Land | Interview Sessions 1 to 3 | 1 | Book Interview Session 1 |  | Client | Client | Released by coach, or by welcome email (starts with Land) | Creates prep task |  | #16 Book Interview Session, or #5 Welcome: starts with Land | Preview | 3 | Interview Session 1
Land | Interview Sessions 1 to 3 | 2 | Prepare for Interview Session 1 | Session 1 workbook | Coach | Peri | Booking made | Ready for session
Land | Interview Sessions 1 to 3 | 3 | Run Interview Session 1 |  | Coach | Peri | Session held | Releases homework | Interview strategy set | #17 Session recap + homework | Preview |  |  | Yes
Land | Interview Sessions 1 to 3 | 4 | Complete Session 1 homework |  | Client | Client | Released by #17 | Sends AI practice email |  | #18 AI practice email | Auto | 3
Land | Interview Sessions 1 to 3 | 5 | Book Interview Session 2 |  | Client | Client | Released by coach | Creates prep task |  | #16 Book Interview Session | Preview | 3 | Interview Session 2
Land | Interview Sessions 1 to 3 | 6 | Prepare for Interview Session 2 | Session 2 workbook | Coach | Peri | Booking made | Ready for session
Land | Interview Sessions 1 to 3 | 7 | Run Interview Session 2 |  | Coach | Peri | Session held | Releases homework |  | #17 Session recap + homework | Preview |  |  | Yes
Land | Interview Sessions 1 to 3 | 8 | Complete Session 2 homework |  | Client | Client | Released by #17 | Sends AI practice email |  | #18 AI practice email | Auto | 3
Land | Interview Sessions 1 to 3 | 9 | Book Interview Session 3 |  | Client | Client | Released by coach | Creates prep task |  | #16 Book Interview Session | Preview | 3 | Interview Session 3
Land | Interview Sessions 1 to 3 | 10 | Prepare for Interview Session 3 | Session 3 workbook | Coach | Peri | Booking made | Ready for session
Land | Interview Sessions 1 to 3 | 11 | Run Interview Session 3 |  | Coach | Peri | Session held | Releases homework |  | #17 Session recap + homework | Preview |  |  | Yes
Land | Interview Sessions 1 to 3 | 12 | Complete Session 3 homework |  | Client | Client | Released by #17 | Sends AI practice email |  | #18 AI practice email | Auto | 3
Land | Mock Interview | 1 | Book Mock Interview |  | Client | Client | Released by coach | Creates prep task |  | #19 Book your mock interview | Preview | 3 | Mock Interview
Land | Mock Interview | 2 | Prepare for mock interview |  | Coach | Peri | Booking made | Ready for session
Land | Mock Interview | 3 | Run and record mock interview | Save recording | Coach | Peri | Session held | Creates Evaluate mock | [5 empty] | Yes
Land | Mock Interview | 4 | Evaluate mock interview | Scorecard for content and delivery; shared via Library and email | Coach | Peri | Mock done | Library link added | Mock interview evaluated | #20 Scorecard ready | Preview
Land | Pre-Interview Prep | 1 | Prepare for pre-interview prep | Repeatable; client books anytime, no release | Coach | Peri | Client books Pre Interview Prep | Ready for session |  |  |  |  | Pre Interview Prep
Land | Pre-Interview Prep | 2 | Run pre-interview prep |  | Coach | Peri | Session held | History | Interview ready (first time) |  |  |  |  | Yes
Land | Offboarding | 1 | Book Offboarding session |  | Client | Client | Released by coach | Creates prep task |  | #21 Book your offboarding | Preview | 3 | Offboarding (30 min)
Land | Offboarding | 2 | Prepare for offboarding |  | Coach | Peri | Booking made | Ready for session
Land | Offboarding | 3 | Run offboarding |  | Coach | Peri | Session held | History | Engagement complete | #22 Closing email, Offboarding packages (keeps 25% off) | Preview

## Packages
IMPORT SPEC
Packages
A package is a group of deliverables. Prices from the current pricing page. Offboarding is included only in All the Way Through and Interview Performance. All the Way Through excludes Prove while it is parked.
Phase | Deliverable | Your SIGNAL DNA | Know Where to Aim | Run the Search | All the Way Through | Resume Rebuild | Foundations | The Proof Project | Job Search Strategy | Interview Performance
| Kind | Bundle and a la carte | Bundle | Bundle | Bundle | A la carte | A la carte | A la carte (parked, do not import) | A la carte | A la carte
| Price | 350 | 800 | 1750 | 2500 | 250 | 500 | 1800 | 1200 | 1500
| Welcome email | #2 starts with Your SIGNAL DNA | #2 starts with Your SIGNAL DNA | #2 starts with Your SIGNAL DNA | #2 starts with Your SIGNAL DNA | #3 starts with Resume Workshop | #3 starts with Resume Workshop | Later | #4 starts with Search | #5 starts with Land
Know | Your SIGNAL DNA Assessment | ✓ | ✓ | ✓ | ✓
Know | Your SIGNAL DNA Report | ✓ | ✓ | ✓ | ✓
Know | Your SIGNAL DNA Decode and Career Path Session | ✓ | ✓ | ✓ | ✓
Build | Resume Workshop |  | ✓ | ✓ | ✓ | ✓ | ✓
Build | Resume |  | ✓ | ✓ | ✓ | ✓ | ✓
Build | Cover Letter |  | ✓ | ✓ | ✓ |  | ✓
Build | LinkedIn Rebuild |  | ✓ | ✓ | ✓ |  | ✓
Prove | The Proof Project (to define) | [6 empty] | ✓
Search | SIGNAL Setup and Job Search Strategy |  |  | ✓ | ✓ |  |  |  | ✓
Search | Networking Campaign |  |  | ✓ | ✓ |  |  |  | ✓
Land | Interview Sessions 1 to 3 |  |  |  | ✓ |  |  |  |  | ✓
Land | Mock Interview |  |  |  | ✓ |  |  |  |  | ✓
Land | Pre-Interview Prep |  |  |  | ✓ |  |  |  |  | ✓
Land | Offboarding |  |  |  | ✓ |  |  |  |  | ✓
Source: prices and inclusions from the WRN pricing page and Peri's decisions in this thread. Pricing page fixes still pending: 300 to 500 contacts becomes 100 to 300; remove AI interview simulator; rename Professional DNA and Career Paths to Your SIGNAL DNA.

## Client Emails
REFERENCE
Client Emails
Preview = coach chooses Send, Edit and send, or Don't send. Only Auto and System emails go out without preview.
# | Email | Phase | Send mode | Status
1 | SOW with Let's Go | Prospect | Preview | To write
2 | Welcome: starts with Your SIGNAL DNA | Onboarding | Preview | Draft exists, revisit
3 | Welcome: starts with Resume Workshop | Onboarding | Preview | To write
4 | Welcome: starts with Search | Onboarding | Preview | To write
5 | Welcome: starts with Land | Onboarding | Preview | To write
6 | Report ready + Decode booking link | Know | Preview | To write
7 | Decode recap + Resume Workshop link (only if package continues into Build; else #23) | Know | Preview | To write
8 | Draft resume ready + Finalize booking link | Build | Edit and send | To write
9 | Resume sign-off request | Build | Preview | To write
10 | Cover letter draft ready (includes framework walkthrough) | Build | Preview | To write
11 | Cover letter sign-off request | Build | Preview | To write
12 | LinkedIn plan ready | Build | Preview | To write
13 | Book your strategy session | Search | Preview | To write
14 | SIGNAL invite | Search | System, sent live | Built, revisit
15 | Networking plan ready + Review Networking Plan link | Search | Auto on share | Built, add link, revisit
16 | Book Interview Session 1 to 3 | Land | Preview | To write
17 | Session recap + homework | Land | Preview | Session 1 exists, revisit; 2 and 3 to write
18 | AI practice email | Land | Auto | Exists, revisit
19 | Book your mock interview | Land | Preview | To write
20 | Scorecard ready | Land | Preview | To write
21 | Book your offboarding | Land | Preview | To write
22 | Closing email, Offboarding packages (keeps 25% off) | Land | Preview | Exists, revisit
23 | Closing email, all other packages (no discount) | Any | Preview | Drafted, revisit